## Project Planner
DAVT
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 60 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Initiation and planning | 1 | 48 | 2 | 47 | 90%
1.1 Software Configuration Management (SCM) | 3 | 2 | 3 | 3 | 100%
1.2 Version Control Systems (VCS) | 3 | 1 | 3 | 1 | 100%
1.3 High-Level Requirements and Scope Definition | 3 | 3 | 3 | 2 | 100%
1.4 Project Team Formation | 1 | 2 | 2 | 2 | 100%
1.5 Requirements Planning | 4 | 1 | 4 | 1 | 100%
1.6 Set Project Team | 3 | 1 | 3 | 2 | 100%
1.7 Initiate Team Meetings | 1 | 48 | 2 | 47 | 90%
1.8 Develop Project Plan | 3 | 4 | 4 | 4 | 100%
1.9 Request Approval | 3 | 1 | 3 | 1 | 100%
1.10 Risk Management Analysis | 3 | 2 | 3 | 2 | 100%
1.11 Evaluation and Reccomendation | 3 | 3 | 4 | 2 | 100%
1.12 Develop Project Chart | 3 | 1 | 3 | 2 | 100%
1.13 Develop Scope | 3 | 2 | 4 | 1 | 100%
1.14 Identify Stakeholders | 3 | 1 | 3 | 1 | 100%
1.15 External/Internal Communication | 3 | 46 | 3 | 46 | 90%
1.16 Time Management | 3 | 2 | 3 | 3 | 100%
1.17 Sponsor Reviews Project Chart | 3 | 1 | 3 | 1 | 100%
1.18 Project Chart Approved | 3 | 1 | 3 | 1 | 100%
Requirements Analysis and Design | 6 | 10 | 5 | 11 | 100%
2.1 Detailed User Requirements | 6 | 4 | 5 | 4 | 100%
2.2 Use Case Identification and Prioritization | 6 | 2 | 6 | 5 | 100%
2.3 User Interface Design and Wireframes | 10 | 3 | 10 | 4 | 100%
2.4 Design Hardware and Software | 13 | 2 | 13 | 2 | 100%
2.5 Validation and Verification | 6 | 2 | 7 | 1 | 100%
2.6 Designs Approved | 15 | 1 | 14 | 2 | 100%
Tool Development | 16 | 10 | 16 | 10 | 100%
3.1 GUI Development | 16 | 6 | 16 | 5 | 100%
3.2 Backend API Development | 18 | 8 | 18 | 7 | 100%
3.3 Database Implementation | 22 | 4 | 22 | 2 | 100%
Testing and Quality Assurance | 24 | 15 | 24 | 15 | 100%
4.1 Unit Testing GUI and APIs | 24 | 3 | 24 | 6 | 100%
4.2 Integration Testing of Components | 24 | 4 | 24 | 6 | 100%
4.3 User Acceptance Testing (UAT) | 27 | 6 | 27 | 6 | 100%
4.4 Validation and Verification | 26 | 3 | 26 | 4 | 100%
4.5 User Feedback | 27 | 12 | 29 | 10 | 100%
4.6 Approved | 33 | 2 | 33 | 3 | 100%
Implementation | 35 | 10 | 35 | 10 | 25%
5.1 Facility Construction | 35 | 5 |  |  | 0%
5.2 Installation | 40 | 2 |  |  | 0%
5.3 Beta Testing | 42 | 3 | 43 | 2 | 75%
Delivery | 42 | 7 |  |  | 0%
6.1 Staff Training | 45 | 4 |  |  | 0%
6.2 Support | 42 | 7 |  |  | 0%