## Gantt
ID | Name | Duration (days) | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 7
|  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1.0 | Project Initiation and planning
1.1 | Software Configuration Management (SCM) | 2 | bar: Week 1 W to Week 1 T
1.2 | Version Control Systems (VCS) | 1 | bar: Week 1 W
1.3 | High-Level Requirements and Scope Definition | 3 | bar: Week 1 W
1.4 | Project Team Formation | 2 | bar: Week 1 M to Week 1 T
1.5 | Requirements Planning | 1 | bar: Week 1 T
1.6 | Set Project Team | 1 | bar: Week 1 W
1.7 | Initiate Team Meetings | -
1.8 | Develop Project Plan | 4 | bar: Week 1 W to Week 2 M
1.9 | Request Approval | 1 | bar: Week 1 W
1.1 | Risk Management Analysis | 2 | bar: Week 1 W to Week 1 T
1.11 | Evaluation and Reccomendation | 3 | bar: Week 1 W to Week 1 F
1.12 | Develop Project Chart | 1 | bar: Week 1 W
1.13 | Develop Scope | 2 | bar: Week 1 W to Week 1 T
1.14 | Identify Stakeholders | 1 | bar: Week 1 W
1.15 | External/Internal Communication | -
1.16 | Time Management | 2 | bar: Week 1 W to Week 1 T
1.17 | Sponsor Reviews Project Chart | 1 | bar: Week 1 W
1.18 | Project Chart Approved | 1 | bar: Week 1 W
2.0 | Requirements Analysis and Design | bar: Week 2 M to Week 3 F
2.1 | Detailed User Requirements | 4 | bar: Week 2 M to Week 2 T
2.2 | Use Case Identification and Prioritization | 2 | bar: Week 2 M to Week 2 T
2.3 | User Interface Design and Wireframes | 3 | bar: Week 2 F to Week 3 T
2.4 | Design Hardware and Software | 2 | bar: Week 3 W to Week 3 T
2.5 | Validation and Verification | 2 | bar: Week 2 M to Week 2 T
2.6 | Designs Approved | 1 | bar: Week 3 F
3.0 | Tool Development | bar: Week 4 M to Week 5 F
3.1 | GUI Development | 6 | bar: Week 4 M to Week 5 M
3.2 | Backend API Development | 8 | bar: Week 4 W to Week 5 F
3.3 | Database Implementation | 4 | bar: Week 5 T to Week 5 F
4.0 | Testing and Quality Assurance | bar: Week 5 T to Week 7 W
4.1 | Unit Testing GUI and APIs | 3 | bar: Week 5 T to Week 6 M
4.2 | Integration Testing of Components | 4 | bar: Week 5 T to Week 6 T
4.3 | User Acceptance Testing (UAT) | 6 | bar: Week 6 T to Week 7 T
4.4 | Validation and Verification | 3 | bar: Week 6 M to Week 6 W
4.5 | User Feedback | - | bar: Week 6 T to Week 7 W
4.6 | Approved | 2 | bar: Week 7 W to Week 7 T
5.0 | Implementation | bar: Week 7 F to Week 7 T
5.1 | Facility Construction | ? | bar: Week 7 F
5.2 | Installation | ? | bar: Week 7 M
5.3 | Beta Testing | ? | bar: Week 7 T
6.0 | Delivery | bar: Week 7 W
6.1 | Staff Training | ? | bar: Week 7 W